## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1.1 | Students management | As an administrator, I want to have a page to look at all students' information so that I can make further adjustments to one user's information | very high | 1 | There is a page that shows all the current students |  | 2023.3.18 | 2023.3.31
1.2 | Courses management | As an adminstrator, I want to have a page to look at all courses' information so that I can make further adjustments to courses | very high | 1 | There is a page that shows all the current courses |  | 2023.3.18 | 2023.3.31
1.3 | User login | As a user, I want to make sure that my information is private and that I am the only person who can view my results. So I want a priavte account and the account is availble for me at anytime | very high | 1 | Registered users can directly log in to the main interface if supply correct ID and PIN |  | 2023.3.18 | 2023.3.31
1.4 | List the module I learned | As a student, I want to know how many courses I have attended exactly. So the basic module information should be listed | very high | 1 | There should have a page link in users' personal interface, when users enter that page, they can see all the courses they are studying or have studied |  | 2023.3.18 | 2023.3.31
2.1 | Change my personal information | As a user, I want to change the password and other personal information of my account to improve the security of my account | medium | 2 | There is a user profile interface that allows users to change their passwords or other personal information |  | 2023.3.18 | 2023.3.31
2.2 | List student's module grades | As a student, I hope not only to know how many courses I have studied, but also to intuitively know the score information of each course | very high | 2 | When users click the grade module, they can see the grade of the course they have completed |  | 2023.3.18 | 2023.3.31
2.3 | Add new or delete users | As an administrator, I want to be able to add or delete or change user baisc information | very high | 2 | Administrators can add or remove a course in course management page. |  | 2023.4.3 | 2023.4.14
2.4 | Add new or delete courses | As an administrator, I want to be able to add or remove a course | very high | 2 | Administrators can add or remove a course in course management page. |  | 2023.4.3 | 2023.4.14
3.1 | Keyword searching | As administrators and users, we want to be able to search quickly to find the results we want | high | 3 | Some interfaces have a search box that displays specific results when you type in a keyword |  | 2023.4.17 | 2023.4.28
3.2 | Change the arrangement of grades | As a student, I want to be able to arrange the grades of the course in order from largest to smallest | medium | 3 | There is a menu of options to arrange information such as grades in descending order |  | 2023.4.17 | 2023.4.28
3.3 | Curriculum schedule | As a student, I want to be able to see the weekly curriculum schedule | medium | 3 | There is an area in the user interface for students to see weekly curriculum schedule |  | 2023.4.17 | 2023.4.28
3.4 | Export students' GPA | As a student, I want to be able to see my GPA for my current completed courses | very high | 3 | Students can export their GPA on the student module grades page |  | 2023.4.17 | 2023.4.28
3.5 | Mask password | As a user, I want my password to be invisible when I log in | low | 3 | The password is masked when the user logs in |  | 2023.4.17 | 2023.4.28
3.6 | Feedback | As a user, I hope to have a feedback function to solve some errors in time and make the software better | medium | 3 | There are areas for user feedback to be submitted |  | 2023.4.17 | 2023.4.28
4.1 | Record personal achievement | As a student, I want to see my experience of winning awards in competitions or exams at school, so I hope to have a page listing some events and awards I have participated in | medium | 4 | There is a page to record students' personal achievements in school |  | 2023.5.1 | 2023.5.12
4.3 | Check for email | As a student, I want to be able to log in to my personal email address to check and send messages | medium | 4 | There is a link to access to students' email |  | 2023.5.1 | 2023.5.12
4.4 | Search for literature | As a student, I want to be able to jump directly to Google Academic webside to facilitate my search for some literature | very low | 4 | There is a link to access to literature searching website |  | 2023.5.1 | 2023.5.12
4.5 | Beautify the application interface | As a developer, I want to beautify the software pages to give users a better user experience | high | 4 | The look and feel of the application interface is improved |  | 2023.5.1 | 2023.5.12