## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1.1 | User managemment | As an administrator, I want to be able to look at all users' information so that I can make further adjustments to one user's information | very high | 1 | There is a page that shows all the current users |  | 2023.3.18 | 2023.3.31
1.2 | Sign and log in | As a user, I want to make sure that my information is private and that I am the only person who can view my results. So I want a priavte account and the account is availble for me at anytime | very high | 1 | New users can jump to the registration interface from the login interface to sign in, and registered users can directly log in to the main interface |  | 2023.3.18 | 2023.3.31
1.3 | List the module I learned | As a student, I want to know how many courses I have attended exactly. So the module information should be listed. | very high | 1 | When users click on the learning module, they can see all the courses they are studying or have studied |  | 2023.3.18 | 2023.3.31
1.4 | Record module grades | As a student, I hope not only to know how many courses I have studied, but also to intuitively know the score information of each course. | very high | 1 | When users click the grade module, they can see the grade of the course they have completed |  | 2023.3.18 | 2023.3.31
2.1 | Change user's information | As an administrator, I want to be able to add or delete or change user baisc information | very high | 2 | There is an edit button in the student information interface. The administrator can change relevant information after clicking the edit button |  | 2023.4.3 | 2023.4.14
2.2 | Change course information | As an administrator, I need to be able to add or remove a course and change the scores of students in a course | very high | 2 | Administrators can add or remove a course or change the grade of a student who has chosen a course |  | 2023.4.3 | 2023.4.14
2.3 | Keyword searching | As administrators and users, they want to be able to search quickly to find the results they want | high | 2 | Some interfaces have a search box that displays specific results when you type in a keyword |  | 2023.4.3 | 2023.4.14
2.4 | Change the arrangement of information | As administrators and users, they want to be able to arrange the grades of the course in order from largest to smallest | medium | 2 | There is a menu of options to arrange information such as grades in descending order |  | 2023.4.3 | 2023.4.14